## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Introduction
| Table 1 | Introduction
Product backlog
| Table 1 | Product backlog
Sprint 1
| Table 1 | Sprint 1
Sprint 2
| Table 1 | Sprint 2

## Introduction
Project Name
What is this? | This workbook is meant to help manage and piroritize the user stories and features using scrum.
How to use and read this document? | Before project start: The product owner is responsible for managing and maintaining the product backlog of user stories.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells that you can edit have a blue background.
Sprints are assumed to be 2 weeks long (10 working days)/
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.

## Product backlog
Project Name
| Organizations | Group 3
| Project | Pageflow
| Product Owner | Gustavo Hernandez
| Scrum Master | Kiana Lang
| Development Team | Fernando Lugo, Bryan Hummel, Ronald Kong
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility
S1 | Authentication & Registration | Implement login and registration UI and backend. | User can log in and register; invalid inputs blocked; JWT/session created. | 1 | 1 | Fernando
S13 | Dev Environment Setup | Set up reproducible development environment and CI/CD pipeline. | Environment documented; CI/CD runs tests on push. | 2 | 1 | Fernando
S1 | Database Schema | Create initial database schema for users, books, orders, and sales. | SQL script creates tables; ERD uploaded; tested with sample data. | 1 | 1 | Gustavo
S1 | Repo Setup | Create GitHub repo with structure and documentation. | Repo has /src/, /docs/, /db/; README with vision and roles. | 1 | 1 | Gustavo
S1 | Scrum Ceremonies | Facilitate planning, standups, and retrospectives. | Planning doc created; standups logged; retro notes documented. | 1 | 1 | Kiana
S4 | Customer Ordering | Design book browsing UI and order placement. | Customers can view books, place orders, and receive confirmation. | 1 | 2 | Gustavo
S4 | Order Confirmation | Validate order confirmation flow. | Orders confirmed with receipt; confirmation logic tested. | 1 | 2 | Fernando
S5 | User Roles & Permissions | Implement role-based access control and user role UI. | Roles defined; access restricted; secure login enforced. | 2 | 2 | Kiana
S7 | Dashboard & Reporting | Develop dashboard for inventory and sales metrics. | Dashboard shows metrics; data updates in real-time. | 2 | 2 | Gustavo
S8 | Book Search | Implement book search with autocomplete. | Search bar with suggestions; handles errors gracefully. | 1 | 2 | Kiana
S16 | Process Returns | Return item UI and inventory update. | Users can return items; inventory reflects changes. | 2 | 2 | Gustavo
S17 | Quality Control | Final testing and debugging of all features. | All Sprint 2 features tested and debugged; ready for demo. | 2 | 2 | All

## Sprint 1
Sprint #1Tracking Sheet
|  | Project |  | Bookstore Inventory and Sales Automation
|  | Sprint # |  | 1
|  | Start date |  | 2025-09-02
|  |  | Total Team Members | 5
[5 empty] | week 1 | [6 empty] | week 2 | [6 empty] | Total Hours
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15
S1-T1 | S1 | Implement login UI (form validation) | Fernando | 6 | 2025-09-02: 2; 2025-09-03: 2; 2025-09-08: 2; 2025-09-09: 2; 2025-09-14: 2 | 10
S1-T2 | S1 | Implement backend login/authentication | Fernando | 8 | 2025-09-04: 4; 2025-09-10: 4; 2025-09-14: 2 | 10
S1-T3 | S1 | Implement registration UI + API | Fernando | 8 | 2025-09-05: 2; 2025-09-06: 2; 2025-09-11: 2; 2025-09-12: 2 | 8
S1-T4 | S1 | Create initial database schema (Users, Books, Orders, Sales) | Gustavo | 6 | 2025-09-07: 2; 2025-09-13: 2; 2025-09-14: 2 | 6
S1-T5 | S1 | Create GitHub repo + structure | Gustavo | 1.5 | 2025-09-06: 0.5; 2025-09-07: 1; 2025-09-12: 0.5; 2025-09-13: 1; 2025-09-14: 2 | 5
S1-T6 | S1 | Facilitate ceremonies (planning, standups, retro) | Kiana | 3.5 | 2025-09-06: 2; 2025-09-12: 2; 2025-09-14: 2 | 6
S1-T7 | S1 | Set up reproducible dev environment and CI/CD pipeline | Fernando | 6 | 2025-09-06: 2; 2025-09-07: 1; 2025-09-12: 2; 2025-09-13: 1; 2025-09-14: 2 | 8
S1-T8 | S1 | Draft Product Backlog | Kiana | 3 | 2025-09-06: 3; 2025-09-12: 3; 2025-09-14: 2 | 8
|  | Remaining units (actual) |  | 80 | 2025-09-02: 79; 2025-09-03: 78; 2025-09-04: 75; 2025-09-05: 72; 2025-09-06: 71; 2025-09-07: 70
|  | Remaining units (ideal) |  |  | 74.2857 | 68.5714 | 62.8571 | 57.1429 | 51.4286 | 45.7143 | 40 | 34.2857 | 28.5714 | 22.8571 | 17.1429 | 11.4286 | 5.7143 | 0
[10 empty] | 0 | 42 | [5 empty] | 0 | 2
[10 empty] | 10 | 0 | [5 empty] | 10 | 0

## Sprint 2
Sprint #2Tracking Sheet
|  | Project |  | Bookstore Inventory and Sales Automation
|  | Sprint # |  | 2
|  | Start date |  | 2025-09-16
|  |  | Total Team Members | 5
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29
S2-T1 | S4 | Design book browsing UI and order placement | Gustavo | 6
S2-T2 | S4 | Validate order confirmation flow | Fernando | 2
S2-T3 | S5 | Implement role-based access control and user role UI | Kiana | 5
S2-T4 | S7 | Develop dashboard for inventory and sales metrics | Gustavo | 3
S2-T5 | S8 | Implement book search with autocomplete | Kiana | 5
S2-T6 | S16 | Return item UI and inventory update | Gustavo | 5
S2-T7 | S17 | Final testing and debugging of all features | All | 4
|  | Remaining units (actual) |  | 80
|  | Remaining units (ideal) |  |  | 74.2857 | 68.5714 | 62.8571 | 57.1429 | 51.4286 | 45.7143 | 40 | 34.2857 | 28.5714 | 22.8571 | 17.1429 | 11.4286 | 5.7143 | 0
[10 empty] | 0 | 30 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0